## Comments
First Floor Renovation Project
Comments
Phased Project
Phase 1
West renovated to Children's Library, Teen space and YS functions
Center - West side of Lobby renovated from column line
Public elevators need to remain accessible
Phase 2
East renovated to new functions
Center - East side of Lobby renovated including center section
General
Ceilings and clouds removed in public spaces, new clouds TBD
Ceilings in staff spaces renovated with new tiles and lighting (TBD this is a minimum)
West end spandrel replaced (south and north TBD)
Entry to West is storefront with auto sliding doors
Under the Sea mobile TBD, other installed art is removed
Lobby terrazzo to remain, entry walk-off TBD
No painting vertical concrete
Concrete patchwork matching/aesthetic concern
Construction noise is a major concern
Worker parking is offsite between 6am and 8pm (with exception of PM - 1 space)
Dumpster location/security
Worker restroom accommodations

## Current
First Floor Renovation Project
West means west of the expansion joint at the public elevators
Center means west of the 1966 building and east of the expansion joint
East means west of the expansion joint at the men's public restroom
Space | Moves to | Comments
WEST
Adult collections | TBD | Some East
Teen space | Stays West
Stage | Reduce space allocation
CENTER
Lobby | Cannot move | Walk-off solution needed at entry
Public restrooms | Cannot move
Adult changing room | TBD - relocated
Security desk/office | TBD - relocated
Gifts & Greetings | Stays Center
Storage | Remove
AV closet | Remove
Information Desk | Stays Center
Check-in/check-out | Stays Center
Circulation work space | TBD Stays Center
Café/Storage | Removed | Electrical panel in closet
Passport office | TBD
Art gallery | Stays Center
Fire command | Cannot move
Circulation workroom | TBD
Managers offices (4?) | TBD Stays Center
Mailroom space | Cannot move | Space allocation
Children's library lobby | Remove
EAST
Old freight elevator lobby
Drive-up window
Back hall storage | TBD
Back hall staff restrooms | TBD
Back hall | TBD | Electrical and lighting panel in hall
Papa bear | West | YS program spaces go West
Mama bear storage | West
Mama bear | West
Mama/baby bear storage | West | YS storage spaces go West
Baby bear | West
YS workroom | West
YS managers offices (3?) | West
YS collections | West
Under the Sea space
Clock Tower space
Exterior patios

## Future
First Floor Renovation Project
West means west of the expansion joint at the public elevators
Center means west of the 1966 building and east of the expansion joint
East means west of the expansion joint at the men's public restroom
Space name | Comments
WEST
Children's Library
Teen space
Stage
YS programming spaces
YS storage spaces
YS workroom
YS managers offices
Public restrooms (M&W)
Family/ADA restroom
Lactation pod
Staff restrooms (?)(M&W)
CENTER
Lobby
Public restrooms
Adult changing room
Security desk/office
Gifts & Greetings
Information Desk
Check-in/check-out
Circulation work space
Passport office
Art gallery
Fire command
Circulation workroom
Circulation storage
Managers offices (4?)
Mailroom space
EAST | Current
Old freight elevator lobby
Drive-up window
TBD Public computers | Under the Sea space | No poke-throughs
TBD Study rooms/space | Clock Tower space
TBD Adult collections | Children's Library
TBD public meeting rooms | Children's programming spaces
TBD | Exterior patios